## Risks
4. Risk Assessment and Mitigation
Risk | Description | Mitigation Strategy
Data Security | Exposure of sensitive information | Use Azure Key Vault and enable data encryption for data at rest and in transit. Implement strict access controls.
Inconsistent Data | Data quality issues due to different formats and sources | Implement data validation and error handling in Azure Databricks. Use standardized data schemas.
System Latency | Delays in processing real-time data | Optimize Databricks clusters, use auto-scaling, and monitor streaming jobs for real-time performance.
Integration Failures | Connectivity issues with external systems (RDS, SOAP API) | Regularly test connectivity, set up failover mechanisms, and use retries for critical connections.
Cloud Cost Overruns | Uncontrolled costs due to over-provisioning | Implement Azure Cost Management to monitor expenses. Regularly review resource usage, and use auto-scaling and right-sizing practices.